## 
| Type | Priority | Severity | Status
| UI | P1 | Low | Open
| Enhancement | P2 | Medium | Closed
| Functional | P3 | High | In Progress
| Show Stopper |  |  | In Test
Tracks
Portfolio Manager
Execution Broker
Trader
Quality Assurance Process
Defect Tracker

## Portfolio Manager
Sl No. | Defect Description | Type | Priority | Severity | Source | Assigned To | Status
1 | Username and password were case insensitive | UI | P2 | Low | Login Page | Piyusha | Closed
2 | Reset Password button and Validation Check | UI | p3 | Low | ForgotPassword window | Abhinav | Closed
3 | Refresh Grid of portfolio was not working fine | Functional | P2 | Medium | PortfolioView window | Jupneet | Closed
4 | Stop Price and Limit Price were not getting disabled as per order type | Functional | p2 | Medium | Create order view | Mavez | Closed
5 | Lookup button was not able to bind to the security name | Functional | p2 | Medium | Create order view | Aakanksha | Closed
6 | Multiple Delete was not working fine | Functional | p2 | Medium | PortfolioView window | Abhinav | Closed
7 | Multiple send for execution and disabling the button | Functional | p2 | Medium | PortfolioView window | Aakanksha | Closed
8 | view edit was not getting binded to edit window | Functional | p2 | Medium | Create order view | Mavez | Closed
9 | Pnl calculation from market Price | Functional | p2 | Medium | PortfolioView window | Piyusha | Closed
10 | Search in Graph and attaching graph with real time market price | Functional | p2 | Medium | Graph Window | Jupneet | In Progress

## Execution Broker
Sl No. | Defect Description | Type | Priority | Severity | Source | Assigned To | Status
1 | Username and password were case insensitive | UI | P2 | Low | Login Page | Paanshul | In Progress
2 | Reset Password button and Validation Check | UI | p3 | Low | ForgotPassword window | Paanshul | Closed
3 | Security Configuration Null value checking | Show Stopper | P3 | High | Trade Price Calculation | Vinay | Closed
4 | Block null exception | Functional | P2 | Medium | Auto Allocation | Ankit | Closed
5 | Mismatch of curent trade price and market price. | Functional | P2 | Medium | Order Execution | Paanshul | Closed
6 | Thread Concurrency | Functional | P1 | High | Auto Allocation | Ankit | Open

## Trader
Sl No. | Defect Description | Type | Priority | Severity | Source | Assigned To | Status
1 | Add To Block Window opens even if no such block exists | UI | P2 | Medium | Add to Block Window | Aanchal | Closed
2 | Lag after every functionality | Functional | P2 | Medium | Main Window | Naman | Closed
3 | Data can be shown using graphs | Enhancement | P3 | Low | Main Window | Rosy | Open
4 | Resize grid functionality | Enhancement | P3 | Low | Main Window | Amandeep | Open
4 | New orders are not shown in filter | Functional | P2 | Medium | Main Window | Bhavika | Closed
5 | Execption occurs if filters are used after selecting an | Functional | P2 | Medium | Main Window | Bhavika | Closed
open order
6 | Validation on limit price and stop price | UI | P2 | Medium | Edit Block Window | Naman | Closed