## Project Overview
Master Data Management System(MDM)
Project Overview
Master Data Management is an application to allow the user to reduce data redundancy by allowing many different business applications to interact with a centralized repository of data.It supports sharing of wide range of data and standardistion of the same.
Client / Project Name | XYZ Inc/ Master Data Management
PID | 97520
S¦A project stage | EAR
Timeframe | 21st Feb 2014 - 27th Feb 2014
Key Client Contacts | Anjali Sharma
Sapient Client Executive | Navneet Batra
Note on B8: This field drives the titles on other tabs.

## Solution Requirements
SOLUTION REQUIREMENTS
1 | 1.1 | User Management | Business Value | Iteration | Owner | In/Out | Description
2 | 1.1.1 | Display login screen for all users | H | 1 | Sapient | In | Login screen will be same for both types of users( admin and user)
2 | 1.1.1.1.1 | Validation of the user | H | 1 | Sapient | In | Should be checked if the user exists in the system
3 | 1.1.1.1.2 | Determine role of user | H | 1 | Sapient | In | Whether user is admin or normal user
3 | 1.1.1.1.3 | Display different pages for admin and normal user | H | 1 | Sapient | In
4 | 1.1.1.1.3.1.1 | Admin User can perform create operation for both Business and Admin Entities and set their privleges | H | 1 | Sapient | In
4 | 1.1.1.1.3.1.2 | Admin User can perform delete operation for both Business and Admin Entities. | H | 1 | Sapient | In
4 | 1.1.1.1.3.1.3 | Admin User can perform edit operation for both Business and Admin Entities. | H | 1 | Sapient | In
1 | 2.1 | Entity Management | Business Value | Iteration | Owner | In/Out | Description
2 | 2.1.1 | Market Business Entity | H
3 | 2.1.1.1 | Ability for admin user and normal user to create new Market | H | 1 | Sapient | In
3 | 2.1.1.2 | Ability for admin user and normal user to view an existing Market | H | 1 | Sapient | In
3 | 2.1.1.3 | Ability for admin user and normal user to update an existing market entity | H | 2 | Sapient | In | The 'updated by' and 'update date' fields are auto populated by the system based on the login credentials
3 | 2.1.1.4 | Ability for admin user to delete an existing market entity | H | 1 | Sapient | In
2 | 2.1.2 | Commodity Business Entity | H
3 | 2.1.2.1 | Ability for admin user and business user to create a commodity entity. | H | 1 | Sapient | In
3 | 2.1.2.2 | Ability for admin user and business user to update a commodity entity. | H | 1 | Sapient | In
3 | 2.1.2.3 | Update Commodity Type | H | 2 | Sapient | In | The 'updated by' and 'update date' fields are auto populated by the system based on the login credentials
3 | 2.1.2.4 | Ability for admin user and business user to delete a commodity entity. | H | 1 | Sapient | In
2 | 2.1.3 | Location Admin Entity | H
3 | 2.1.3.1 | Ability for admin user to create a location entity. | H | 1 | Sapient | In
3 | 2.1.3.2 | Ability for admin user and business user to view a location entity. | H | 1 | Sapient | In
3 | 2.1.3.3 | Ability for admin user to update a location entity. | H | 2 | Sapient | In | The 'updated by' and 'update date' fields are auto populated by the system based on the login credentials
3 | 2.1.3.4 | Ability for admin user to delete a location entity. | H | 1 | Sapient | In
2 | 2.1.4 | Currency Admin Entity | H
3 | 2.1.4.1 | Ability for admin user to create a currency entity. | H | 1 | Sapient | In
3 | 2.1.4.2 | Ability for admin user and business user to view a commodity entity. | H | 1 | Sapient | In
3 | 2.1.4.3 | Ability for admin user to update a commodity entity. | H | 2 | Sapient | In | The 'updated by' and 'update date' fields are auto populated by the system based on the login credentials
3 | 2.1.4.4 | Ability for admin user to delete a commodity entity. | H | 1 | Sapient | In
1 | 3.1 | Business Entity Mapping | Business Value | Iteration | Owner | In/Out | Description
2 | 3.1.1 | Allows Entity Type Selection |  |  |  | In | User Will Select the Entity To Be Worked Upon
2 | 3.1.2 | Market Entity |  |  | Sapient | In
3 | 3.1.2.1 | Create New Entity Mapping |  |  | Sapient |  | User can create New Market Entity Mapping
4 | 3.1.2.1.1 | Allows Entity Mapping Creation | H | 1 | Sapient | In
4 | 3.1.2.1.2 | Supports Duplicate Entity Mapping String Checking | H | 1 | Sapient | In
4 | 3.1.2.1.3 | Supports Default Entity Mapping String Checking | L | 2 | Sapient | In
4 | 3.1.2.1.4 | Support Source System Checking | H | 2 | Sapient | In
3 | 3.1.2.2 | Edit Entity Mapping |  |  | Sapient
4 | 3.1.2.2.1 | Allows Entity Mapping Search | H | 1 | Sapient | In
4 | 3.1.2.2.2 | Allows Entity Mapping Editing | H | 1 | Sapient | In
4 | 3.1.2.2.3 | Supports Duplicate Entity Mapping String Checking | H | 2 | Sapient | In
4 | 3.1.2.2.4 | Supports Default Entity Mapping String Checking | L | 2 | Sapient | In
4 | 3.1.2.2.5 | Supports No Mapping Exist Checking | H | 2 | Sapient | In
4 | 3.1.2.2.6 | Support Source System Checking | H | 2 | Sapient
3 | 3.1.2.3 | Delete Entity Mapping |  |  | Sapient | In
4 | 3.1.2.3.1 | Allows Entity Mapping Search | H | 1 | Sapient | In
4 | 3.1.2.3.2 | Allows Entity Mapping Deletion | H | 1 | Sapient | In
4 | 3.1.2.3.3 | Supports No Mapping Exist Checking | H | 2 | Sapient | In
4 | 3.1.2.3.4 | Support Source System Checking |  | 2 |  | In
3 | 3.1.2.4 | Search Entity Mapping |  |  | Sapient
4 | 3.1.2.4.1 | Allows Mapping String Based Search |  | 1 | Sapient | In
4 | 3.1.2.4.2 | Supports No Mapping String Checking |  | 2 | Sapient | In
2 | 3.1.3 | Commodity Entity |  |  | Sapient
3 | 3.1.3.1 | Create New Entity Mapping |  |  | Sapient
4 | 3.1.3.1.1 | Allows Entity Mapping Creation | H | 1 | Sapient | In
4 | 3.1.3.1.2 | Supports Duplicate Entity Mapping String Checking | H | 1 | Sapient | In
4 | 3.1.3.1.3 | Supports Default Entity Mapping String Checking | L | 2 | Sapient | In
4 | 3.1.3.1.4 | Support Source System Checking | H | 2 | Sapient | In
3 | 3.1.3.2 | Edit Entity Mapping |  |  | Sapient
4 | 3.1.3.2.1 | Allows Dropdown Based Entity Mapping Search | H | 1 | Sapient | In
4 | 3.1.3.2.2 | Allows Entity Mapping Editing | H | 1 | Sapient | In
4 | 3.1.3.2.3 | Supports Duplicate Entity Mapping String Checking | H | 2 | Sapient | In
4 | 3.1.3.2.4 | Supports Default Entity Mapping String Checking | L | 2 | Sapient | In
4 | 3.1.3.2.5 | Support Source System Checking | H | 2 | Sapient | In
3 | 3.1.3.3 | Delete Entity Mapping |  |  | Sapient
4 | 3.1.3.3.1 | Allows Entity Mapping Search from Dropdown List | H | 1 | Sapient | In
4 | 3.1.3.3.2 | Allows Entity Mapping Deletion | H | 1 | Sapient | In
4 | 3.1.3.3.3 | Supports No Mapping Exist Checking | H | 2 | Sapient | In
4 | 3.1.3.3.4 | Support Source System Checking |  | 2 | Sapient | In
3 | 3.1.3.4 | Search Entity Mapping |  |  | Sapient
4 | 3.1.3.4.1 | Allows Mapping String Based Search | H | 1 | Sapient | In
4 | 3.1.3.4.2 | Supports No Mapping String Checking | H | 2 | Sapient | In
2 | 3.1.4 | Search Entity Funcionality |  |  | Sapient
3 | 3.1.4.1 | Allows Search All | H | 1 | Sapient
3 | 3.1.4.2 | Allows Filter Based Search |  |  | Sapient
4 | 3.1.4.2.1 | Allows Location Based Search | H | 2 | Sapient | In
4 | 3.1.4.2.2 | Allows Currency Based Search | H | 2 | Sapient | In
4 | 3.1.4.2.3 | Allows Commodity Based Search | H | 2 | Sapient | In
4 | 3.1.4.2.4 | Allows Market Based Search | H | 2 | Sapient | In

## Client Responsibilites
Level (0 - 6) | Item # | Item | Notes | Supporting Documentation
0 | R1 | CLIENT RESPONSIBILITIES
1 | R1.1 | Technology
2 | R1.1.1 | Dot Net is the technology to be used.
2 | R1.1.2 | Obtaining the license for database server will be client's responsibility
2 | R1.1.3 | Client will be responsible to setup the dummy data for final performance testing
1 | R1.2 | Functionality
2 | R1.2.1 | Client will help Sapient understand the existing functionality of the application and what is desired
2 | R1.2.2 | Client will provide the system test cases to Sapient
2 | R1.2.3 | Client will provide the dummy test data for final performance testing
1 | R1.3 | Project Management
2 | R1.3.1 | Client will attend all iteration checkpoints
2 | R1.3.2 | Client will clarify all queries of the development team with respect to the requirements
2 | R1.3.3 | Client will help Sapient understand the business functionality by participating in the Fusion Workshops.
2 | R1.3.4 | Client will sign off on all planned artifacts within a decided timeline
Note on B2: Set the level from 0 - 6 (highest - lowest) to associate with a hierarchy. Row formatting and shading is associated with these values. In addition, the level is used to determine the item number.
Note on C2: Maintain a unique numbering scheme and freeze this column once Scope is closed. The items will be automatically numbered when using the Renumber tool.
Note on D2: Capture a concise description of the assumption
Note on F2: Include a reference to any relevant supporting documentation.

## Deliverables & Services
Level (0 - 6) | Item | Item | Business Value | Risk/Complexity | Owner | Description | Supporting Documentation or Bounding Assumptions | Dependent on
0 | D1 | PROJECT MANAGEMENT
1 | D1.1 | Planning and tracking |  |  | Sapient | All core functions and standard deliverables including high level plan, release plan, and iteration plans
1 | D1.2 | Risk and issue management |  |  | Sapient | Basic tracking and management of issues and risks, including periodic review and reporting
1 | D1.3 | Partner relationship and communication |  |  | Sapient | All relevant communications with partners, including iteration checkpoint meetings, status reports, and communication plan
0 | D2 | Master Data Management
1 | D2.2.3 | Information Architecture |  |  |  | Defines the underlying organizational structure and complex relationships within a user experience and a system of content, and includes organization,navigation, and interactions.
2 | D2.2.3.1 | Personas(Normal User and Admin User) | High | Medium | Sapient | Fictional users that represent each archetypal class of users. Each persona is a real person with a name and roles.Each role has a specific responsibility which is decided by the admin.
3 | D2.2.3.2 | Use Cases | High | Medium | Sapient | Listing of high-level requirements and/or user tasks across all applications and aspects of the business.
3 | D2.2.3.3 | Wire Frames | Medium | Low | Sapient | Basic visual guide used to suggest the layout and placement of fundamental design elements in the interface design. Also defines the positioning of global and secondary levels of navigation. Wireframes may suggest a basic visual layout, but do not dictate a specific appearance.
1 | D2.2.5 | Content Strategy
2 | D2.2.5.2 | Content Matrix | Medium | High | Sapient | The heart and soul of content documentation. A comprehensive Word table or Excel spreadsheet that tracks content needs, placement, scheduling, sourcing, and more. It evolves over the project lifecycle.
2 | D2.2.5.3 | Taxonomy and Nomenclature | Low | Low | Sapient | A list of all the technical terms and abbreviations used in the entire application supplemented with their explanation.
1 | D2.4 | Front-End Development
2 | D2.4.2 | Application Development
3 | D2.4.2.1 | .net Framework | High | High | Sapient | .NET Framework is a software framework developed by Microsoft that runs primarily on Microsoft Windows. It includes a large library and provides language interoperability (each language can use code written in other languages) across several programming languages.
3 | D2.4.2.2 | WPF Development | High | High | Sapient | Windows Presentation Foundation is a graphical subsystem for rendering user interfaces in Windows-based applications by Microsoft. WPF attempts to provide a consistent programming model for building applications and separates the user interface from business logic
Note on A3: Set the level from 0 - 6 (highest - lowest) to associate with a hierarchy. Row formatting and shading is associated with these values. In addition, the level is used to determine the item number.
Note on B3: Maintain a unique numbering scheme and freeze this column once Scope is closed. The items will be automatically numbered when using the Renumber tool.
Note on C3: Capture a concise description of the requirement. Based on your editing preferences, you may want to use multiple columns here instead of one (with tabs). Feel free to insert as many columns as needed (you will need to adjust printing).
Note on D3: Indicate the business value of this item taking into consideration user value (where applicable).
Note on E3: Indicate the complexity of this item.
Note on F3: Identify the high-level entity responsible for this. Explicitly enter critical components of the system that are not owned by Sapient.
Note on G3: Enter a more detailed description of this item (as needed)
Note on H3: Capture a reference to the detailed specifications for this item. Include specific document name and chapter or section reference. When creating an Implementation estimate, if this is not available, you must include bounding assumptions regarding the item (such as number of screens. fee
Note on I3: Create dependencies between line items, so that you can identify potential problems when you want to delete or scope out an item. Enter in this column the IDs of all items which depend upon this. Do this later in the process so that line numbers will be moderately stable.

## Assumptions
Level (0 - 6) | Item | Item | Notes | Supporting Documentation
0 | A1 | ASSUMPTIONS
0 | A1 | Assumption is that the Globalization requirement is for English.
0 | A2 | Client Participation
1 | A2.1 | Client participation will be required during the user testing phase
1 | A2.2 | During the development phase on client will be required for issue resolution twice a week.
1 | A2.3 | During the user testing phase, clients will be required for issue resolution twice a week.
1 | A2.4 | The client will provide dummy data for testing during UAT phase.
0 | A3 | Technology
1 | A3.1 | The technical solution designed should incorporate future needs of integrating with suppliers.
1 | A3.2 | The MDM will need to be integrated with all the trading/reporting applications so that all the common data can be brought into the system and updated as per the requirements.
0 | A4 | Facilities
1 | A4.1 | All implementation activities will be conducted at Sapient itself.
Note on B3: Set the level from 0 - 6 (highest - lowest) to associate with a hierarchy. Row formatting and shading is associated with these values. In addition, the level is used to determine the item number.
Note on C3: Maintain a unique numbering scheme and freeze this column once Scope is closed. The items will be automatically numbered when using the Renumber tool.
Note on D3: Capture a concise description of the assumption
Note on F3: Include a reference to any relevant supporting documentation.